## Timeline
Timeline | Content | Goal Date | Accomplished
1 | Look up and research NLP tools. Look for libraries. Research ways to store data to files so we don’t have to build every time. | 2014-02-22
2 | Categorize questions to be answered. Can we string-match the question? Can we look at sentence structure? syntax tree? | 2014-02-22
3 | Try to solve easy questions | 2014-02-25
4 | Try to solve medium questions | 2014-03-01
5 | Begin developing questions: how to create fluent syntactically-correct questions? | 2014-03-08
6 | Try to solve hard questions | 2014-03-15
7 | Try to create hard questions to stump other people. | 2014-03-22
8 | COMPLETE PROJECT | 2014-04-01
9
10
11
12
13
14
15
16
17
18
19
20
21

## Checklist
Parse article files

## Timesheet
Date | Things we accomplished
2014-02-22

## Ideas
| Ideas | Problems | Resolution
| Try to build a database beforehand and store it locally in the home folder. Then main project will run independently, using those databases we built. | pronouns??? | Don’t worry about them for now.
dict to .csv and back for Python (Aaron)
How to store the article files when we train our model.
CURRENT MODEL | First, parse sentence. Then convert to 3-grams.